|  | LIFE + Environment Policy and Governance Project Number: LIFE10 ENV/GR/594 Duration: 01/09/11–31/08/15 |
| --- | --- |

Project: Best practices for agricultural wastes (AW) treatment and reuse in the Mediterranean countries, www.wastereuse.eu

March 31, 2015

Chania, Greece

# Subject: “Activities carried out during March 2015”

- In the line of Action 5, the effect of combined organic and inorganic fertilization on barley and wheat growth (second cereal cultivation) in open field is evaluated. Soil samples from the different experimental plots where barley and wheat seeds were shown have been collected and analyzed for total nitrogen and nitrate content in order to assess the top-dressing fertilization to be applied in the different treatments.

In Action 6, cultivation of lettuce, rocket, lamb’s lettuce, basil, rosemary and cabbage was implemented in greenhouse and in open field. Data collected are considered to define the effect of different factors (compost application rate, addition of zeolite or fertilizer) on biomass production of vegetables and aromatic plants. All trials were completed so far and data are under evaluation with regards to cabbage and rosemary cultivation trials.

Collection of experimental data from demonstration Actions 5 and 6 is in progress. These data are sent by Spanish and Italian partners to TUC and SIGNOSIS and are considered in the line of Actions 7 and 8.

Six deliverables are prepared in the line of Actions 5 and 6, according to the proposal timetable.

- In the line of Action 7, updated data collected from Spanish and Italian partners are considered. Deliverables regarding Life Cycle Analysis (LCA) for all processes carried out in Italy and Spain, risk analysis and techno-economical and environmental assessment of the main processes considered, are revised.

- In the line of Action 9, various dissemination activities are implemented:

- The project website www.wastereuse.eu, the Facebook (https://www.facebook.com/ WasteReuse Project? fref=ts) and Twitter (@WasteReuse) fan pages are continuously updated.

- Visits of farmers and stakeholders at demonstration areas in Spain and Italy are in progress.

- A joint paper is prepared and will be presented at the 3rd International Symposium on Organic Matter Management and Compost Use in Horticulture http://www.verticesur.es/congresos/CFH2015/, Murcia, Spain, 20-24 April 2015. Three more papers are prepared to be presented in conferences or submitted for publication in international scientific journals.

- Wastereuse conference “Towards a Sustainable Use of Agricultural Waste” will take place on May 12, 2015 in Brussels, Belgium; challenges, incentives and benefits for sustainable agriculture will be discussed. Speakers/participants are invited and a draft conference program has been prepared by SIGNOSIS.